## Overview
NEPTUNE — Project Overview
Quantitative Risk Intelligence Platform ¦ Iridium Capital Management
PROJECT DESCRIPTION
Neptune is Iridium's quantitative risk intelligence platform — a cloud-based system that maintains real-time beta neutrality on the long book, decomposes factor exposures, optimises the systematic short book via a universe-scanning MIQP solver, and tracks live P&L across all positions. The Optimizer Engine is Neptune's core proprietary module: a two-pass solver that first accounts for discretionary shorts and then selects and sizes the systematic short book to neutralise residual beta and factor risk.
IRIDIUM PRODUCT SUITE
Project | Type | Description | Status
CATO | Desktop (Electron) | SEC EDGAR activism intelligence, insider trading, proxy governance data | Active
Mercury | Web / Cloud | EDGAR XBRL financial data connector; fundamental metrics for the investable universe | Active
Neptune | Cloud | Quantitative risk intelligence and portfolio management platform | Active
Tacitus | Cloud (SaaS) | Quantitative activist screener and Persona Engine | Planning
NEPTUNE OBJECTIVES
# | Objective | Description
1 | Beta Neutrality Engine | Maintain real-time market neutrality on the long book via continuous EWMA/Vasicek/Dimson beta estimation and systematic short book construction.
2 | Universe-Scanning Optimizer | Scan the Russell 3000 shortable universe and solve a two-pass MIQP to select and size the systematic short book that minimises residual beta and factor tracking error.
3 | Multi-Factor Exposure Monitor | Decompose portfolio exposures across five factors (Market, Size, Value, Momentum, Sector) and flag breaches against per-portfolio limits.
4 | Live P&L Engine | Mark-to-market P&L across all positions with FIFO/AVCO/Specific-Lot cost basis tracking, split by Long / Systematic Short / Discretionary Short.
5 | Paper Portfolio Engine | Clone any live portfolio, diverge from it, and run the full risk and hedging stack on paper — enabling PM experimentation and analyst idea evaluation.
6 | Book of Books | Aggregate risk view across all live portfolios: notional-weighted firm-level beta, factor exposures, and cross-portfolio netting.
7 | CATO / Tacitus Integration | Receive short candidate flags from Tacitus screener; supply risk overlay (borrow cost, short interest, liquidity) back to Tacitus and CATO.

## Build Roadmap
NEPTUNE — Build Roadmap
Phased buildout plan ¦ All phases subject to revision
Phase | Workstream | Task | Description |  | Priority | Effort | Status | Notes
Phase 0 Foundation | Architecture | Define cloud stack | Select cloud provider (AWS/GCP/Azure), database engine (PostgreSQL + TimescaleDB), task queue (Celery + Redis), and API framework (FastAPI). Define dev/staging/prod environments. | None | Critical | 2w | Not Started | Recommend AWS + RDS + ElastiCache
| Architecture | PostgreSQL + TimescaleDB schema | Design the Neptune schema: portfolios, positions, lots, beta_snapshots (hypertable), factor_exposures, optimizer_runs, optimizer_positions, pl_snapshots (hypertable), firm_snapshots (hypertable), universe_members, universe_filters, ideas, audit_log. | Cloud stack selected | Critical | 1w | Not Started
| Architecture | Auth & RBAC design | JWT + OAuth2 with four roles: CIO (Book of Books default), PM (assigned portfolios), Analyst (paper portfolios), Admin. All endpoints gated via require_role() dependency. | None | Critical | 1w | Not Started
| Architecture | requirements.txt & Docker | Pin all backend dependencies in requirements.txt (FastAPI, SQLAlchemy, cvxpy, Celery, yfinance, etc.). Docker Compose for local dev; Windows-compatible (requirements.txt install, not pyproject.toml). | None | Critical | 1w | Not Started | Use requirements.txt — avoids setuptools.backends.legacy errors on Windows
| Integrations | Tacitus connector — receive | Build inbound API endpoint to receive short candidate flags and conviction scores from Tacitus. Store in neptune.tacitus_signals table with run_id and timestamp. | Schema complete | High | 1w | Not Started | Define data contract jointly with Tacitus team
| Integrations | CATO connector — risk overlay push | Build outbound push to CATO: Neptune sends per-name risk overlay (borrow cost, short interest %, liquidity score, volatility) for any ticker CATO flags as an activism candidate. | Schema complete | Medium | 1w | Not Started
Phase 1 Beta Engine | Market Data | yfinance price ingestion | Build Celery task for daily price ingestion via yfinance. Store OHLCV in TimescaleDB. Stale price circuit breaker: 10s liquid, 60s OTC. Phase 2+: Bloomberg B-PIPE/SAPI. | Phase 0 complete | Critical | 2w | Not Started | Synthetic prices sufficient for engine/UI dev; Finnhub/Alpaca for live feed testing
| Beta Engine | EWMA beta computation | 252-day exponentially weighted regression vs SPY. Lambda = 0.94. Run nightly via Celery after market close. Store per-position per-portfolio in beta_snapshots hypertable. | Price ingestion live | Critical | 2w | Not Started | Default beta method
| Beta Engine | Vasicek shrinkage | β_vasicek = w·β_ewma + (1−w)·1.0, where w is inversely proportional to estimation variance. Bloomberg 'Adjusted Beta' equivalent. | EWMA live | High | 1w | Not Started
| Beta Engine | Dimson adjustment | Sum of lagged/lead market return coefficients for k = −1, 0, +1. Critical for illiquid activist targets with asynchronous price responses. | EWMA live | High | 1w | Not Started
| Beta Engine | Forward beta override | PM-set per-position forward beta override. Overrides all model outputs for that position in the optimizer. Logged to audit_log with before/after state. | EWMA live | High | 0.5w | Not Started
| Factor Data | Ken French factor loading | Pull FF5 + Momentum factor data from Ken French Data Library. Compute per-security factor loadings using rolling 60-day regression. Store in factor_exposures table. | Price ingestion live | Critical | 2w | Not Started | Factor data: Kenneth French Data Library (free)
Phase 2 Universe & Optimizer | Universe | Universe construction | Build investable shortable universe from Russell 3000. Apply configurable filters: min_adv_30d ($10M), min_market_cap ($500M), max_borrow_cost_bps (50), max_short_interest_pct (20%). Hard-exclude any ticker held long in any live portfolio. | Phase 1 complete | Critical | 2w | Not Started | Filter changes require CIO approval before taking effect
| Universe | Universe filter change approval flow | PM proposes filter change → stored as pending in universe_filter_changes → CIO approves/rejects → approved changes take effect from next scheduled run. Full audit trail. | Universe construction | High | 1w | Not Started
| Optimizer | Two-pass QP optimizer (unconstrained) | Pass 1: compute residual beta and factor exposures after long book + discretionary shorts. Pass 2: unconstrained QP to select and size systematic short book minimising tracking error. Use cvxpy + CLARABEL. | Universe live, factor loadings | Critical | 3w | Not Started | Normalize dollar quantities by long_aum before passing to solver for numerical conditioning
| Optimizer | MIQP capped runs (complexity frontier) | Extension: add binary selection variables and position count cap (N≤50/20/10) to produce capped MIQP runs. Use cvxpy GLPK_MI. Compute complexity-quality frontier: tracking error, net beta, factor breaches at each cap level. | QP optimizer live | High | 2w | Not Started | Greedy+QP approximation as fallback if GLPK_MI unavailable; flag for Phase 3 handoff
| Optimizer | Sector concentration flagging | Flag if any GICS sector exceeds 40% of total short notional (soft warning on unconstrained, hard constraint option on capped runs). Store sector breakdown per optimizer_run. | QP optimizer live | High | 1w | Not Started
| Optimizer | Hedge recommendation & approval flow | Optimizer output stored as hedge_recommendations with status pending. PM approves/rejects per run (or per position). CIO can approve discretionary shorts. Nightly Celery schedule + on-demand PM trigger. | QP optimizer live | Critical | 2w | Not Started | API always returns cached results — no synchronous optimization in request handlers
Phase 3 P&L Engine | P&L | Position Manager CRUD | FastAPI endpoints for position entry, sizing, and lot tracking. Support FIFO (default), AVCO, and Specific Lot cost basis per position. Track every lot with entry price, date, quantity, and cost basis method. | Phase 2 complete | Critical | 2w | Not Started
| P&L | Live P&L computation | Four simultaneous P&L dimensions per position: Day P&L, Total (ITD) P&L, Unrealised P&L, Realised P&L. FX P&L always tracked separately. Reporting split by Long / Systematic Short / Discretionary Short. | Position Manager | Critical | 3w | Not Started
| P&L | WebSocket price pipeline | Price feed → Redis pub/sub → Position Calculator → TimescaleDB → WebSocket push to frontend. Target <400ms end-to-end. Stale price circuit breaker enforced at calculator layer. | Position Manager | Critical | 2w | Not Started | Phase 1: yfinance polling; Phase 2: Bloomberg streaming
| P&L | Multi-currency support | FX P&L always tracked as a separate column. All P&L reported in portfolio base currency (default USD). FX-adjusted beta calculations deferred to Phase 2+. | Live P&L | Medium | 1w | Not Started | Initial build: USD-denominated US equities only
Phase 4 Live Dashboard | UI | React scaffold (Fluent 2 + Deep Ocean) | React 18 + TypeScript + Tailwind CSS + @fluentui/react-components. Design system: Fluent 2 layout (module tabs top, sidebar sub-nav, gear icon for settings). Color palette: Deep Ocean (bg #0a0e1a, accent #3b82f6, secondary #818cf8). Typography: Outfit (display), Inter (body), IBM Plex Mono (numerics). | Phase 3 complete | Critical | 2w | Not Started | Reference: CATO shell architecture for layout grammar
| UI | Live blotter UI | Blotter tab with Long Book / Systematic Short Book / Discretionary Short Book sub-panels. Columns: Ticker, Name, Beta, Notional, Day P&L, Total P&L, Unrealised P&L, Realised P&L, Cost Basis Method. IBM Plex Mono for all numeric columns. | React scaffold | Critical | 3w | Not Started
| UI | Risk dashboard | Risk tab: Beta monitor (net beta gauge, tolerance band), factor exposure table (5 factors with OK/WATCH/BREACH badges), optimizer output panel (frontier chart, unconstrained vs capped comparison), universe filter status. | React scaffold, Optimizer | Critical | 3w | Not Started
| UI | Hedge approval UI | Optimizer tab: PM reviews unconstrained and capped optimizer runs side-by-side. Approve/reject individual positions or full runs. Pending approvals count displayed in top bar. CIO override available. | React scaffold, Optimizer | High | 2w | Not Started
Phase 5 Paper Portfolios & Book of Books | Paper Engine | Portfolio clone endpoint | POST /portfolios/{id}/clone: snapshot all longs, all discretionary shorts, and current systematic short book at a timestamp. Paper flag (is_paper=true) propagates through all downstream tables. | Phase 4 complete | Critical | 1w | Not Started | Paper portfolios never route orders anywhere
| Paper Engine | Paper portfolio optimizer integration | Optimizer re-runs automatically on the paper book after every analyst position change. Analyst cannot directly modify the systematic short book — only indirectly via long book changes. This is the learning mechanism. | Clone endpoint | Critical | 2w | Not Started
| Paper Engine | P&L divergence view | Track paper P&L vs live from clone date. Per-position contribution and factor attribution. PM can see how analyst decisions would have performed vs the live book. | Paper optimizer | High | 2w | Not Started
| Book of Books | Multi-portfolio aggregation engine | Firm-level beta: β_firm = Σ(N_i × β_i) / Σ(N_long) across all live portfolios. Notional-weighted factor exposures. Cross-portfolio netting for same-ticker long/short across portfolios. | Phase 4 complete | Critical | 2w | Not Started | Paper portfolios excluded from firm-level aggregation by default
| Book of Books | Book of Books dashboard UI | CIO default landing page: Portfolio Matrix (every live portfolio as row; columns: Net Beta, Beta Status, Long Notional, Systematic Short Notional, Discretionary Short Notional, Hedge Ratio, 5 factor exposures). Click row to drill into portfolio. Firm Summary Strip persistent in header. | Aggregation engine | Critical | 3w | Not Started

## Risk & Factor Model
NEPTUNE — Risk & Factor Model
Beta estimation methods and five-factor exposure decomposition
BETA ESTIMATION METHODS
Method | Description | Formula / Parameters |  | Data Source | Phase | Notes
EWMA | Exponentially weighted regression vs SPY/benchmark. Fast to respond to regime changes. | λ=0.94, 252-day lookback |  | yfinance / Bloomberg | Phase 1 | Default method for all portfolios
Vasicek Shrinkage | β_vasicek = w·β_ewma + (1−w)·1.0, where w is inversely proportional to estimation variance. | w = σ²_prior / (σ²_prior + σ²_OLS) |  | Derived from EWMA | Phase 1 | Bloomberg 'Adjusted Beta' equivalent
Dimson Adjustment | Sum of lagged and leading market return coefficients. Handles illiquid stocks. | β_dimson = Σβ_lag(k) for k=−1, 0, +1 |  | yfinance / Bloomberg | Phase 1 | Critical for activist targets with asynchronous pricing
Forward Override | PM-set manual beta override per position. Overrides all model outputs for that position. | PM input — stored in positions.forward_beta |  | Manual entry | Phase 1 | Logged to audit_log with before/after state
Kalman Filter | Beta as a latent state variable updated with each new return observation. | State-space model; Kalman gain auto-tunes |  | yfinance / Bloomberg | Phase 3+ | Current best practice — deferred post-Phase 1
FIVE-FACTOR MODEL
Factor | Description | Data Source | Direction | Portfolio Limit (default) | Firm Limit | Notes
Market (Rm-Rf) | Sensitivity to broad market returns (benchmark: SPY). | Ken French / yfinance | Minimise abs exposure | Net β within ±0.050 | ±0.030 | Primary optimizer objective
Size (SMB) | Small-minus-big: exposure to size premium. | Ken French Data Library | Neutral | ±0.20 | ±0.15
Value (HML) | High-minus-low: book-to-market exposure. | Ken French Data Library | Neutral | ±0.20 | ±0.15
Momentum (MOM) | Prior 12-month return momentum exposure. | Ken French Data Library | Neutral | ±0.20 | ±0.15
Sector (GICS) | GICS sector concentration in the short book. | GICS classifications | Max 40% per sector | 40% of short notional | 35% | Soft warning on unconstrained; hard constraint on capped runs

## Optimizer Spec
NEPTUNE — Optimizer Specification
Two-pass MIQP universe-scanning optimizer ¦ cvxpy + CLARABEL / GLPK_MI
TWO-PASS OPTIMIZER LOGIC
Pass 1 | Compute residual exposures | Sum dollar-beta and factor exposures across the long book. Add discretionary short contributions (their notionals are negative, so they reduce the residual burden). Residual = what the systematic short book must neutralise.
Pass 2 | Optimize systematic short book | Universe-scanning QP/MIQP: select securities from the filtered shortable universe and size them to minimise tracking error vs. residual. Primary output: unconstrained optimal book (no position count limit). Secondary: capped runs at N≤50/20/10 for complexity-quality frontier.
Secondary | Discretionary suggestions | Flag discretionary shorts where a resize would improve hedge efficiency by >10%. Stored as recommendation_type = DISCRETIONARY_SUGGESTION. Never auto-applied. PM sees these as advisory annotations on their positions.
OPTIMIZER CONSTRAINTS
Constraint | Type | Formula / Rule | Default Value | Configurable | Applies To | Notes
Beta neutrality | Hard | ¦residual_beta_dollar − Σ(w_i × β_i)¦ ≤ tol × long_aum | tol = 0.050 | Yes — per portfolio | All runs | Primary optimization target
Factor limits | Hard | ¦residual_factor[f] − Σ(w_i × load_i[f])¦ ≤ limit[f] | ±0.20 per factor | Yes — per factor | All runs | Five factors independently
Position size floor | Hard | w_i ≥ 0 | 0 (no short floor) | No | All runs | Positions are notional (positive = short notional)
Position size ceiling | Hard | w_i ≤ max_pos_wt × long_aum | 15% of long AUM | Yes | All runs
Position count cap | MIQP | z_i ∈ {0,1}; w_i ≤ z_i × max_pos_wt × long_aum; Σz_i ≤ N_cap | Unconstrained (no cap) | Yes — PM selects N | Capped runs only | Makes problem MIQP; use GLPK_MI solver
Sector concentration | Soft | Any GICS sector ≤ 40% of total short notional | 40% flag threshold | Yes | All runs | Hard constraint option on capped runs if PM enables
Long-book exclusion | Hard | No ticker held long in any live portfolio | Always enforced | No | All runs | Enforced by runtime join — not static list
Borrow constraint | Hard | max_borrow_cost_bps filter applied in universe construction | 50 bps | Yes — CIO approval | Universe filter | Applied pre-optimization in universe filter step

## Integrations
NEPTUNE — Integration Specifications
Data flows between Neptune, CATO, Mercury, and Tacitus
CATO — DATA FLOWS
Direction | Data Element | Content | Mechanism | Usage in Neptune
← IN | Short opportunity flags | Named companies flagged by CATO activism campaigns as potential re-targets; board composition changes | Weekly ETL from CATO activism.db | Supplementary signal for discretionary short sourcing
← IN | Governance signals | Board tenure, classified board, poison pill, say-on-pay outcomes — for cross-referencing systematic short candidates | Weekly ETL from CATO proxy.db
→ OUT | Risk overlay per ticker | For any ticker active in a CATO campaign: borrow cost %, short interest % of float, liquidity score, 30-day volatility | Neptune API → CATO API or direct DB | Enables CATO to display risk context on company pages
→ OUT | Short book composition | Current systematic short book tickers and notionals — CATO can flag if Neptune is short a name that is also an active campaign target | Post-run push | Cross-system conflict detection
TACITUS — DATA FLOWS
Direction | Data Element | Content | Mechanism | Usage in Neptune
← IN | Short candidate list | Companies scoring high on inverted Tacitus conviction score: ticker, composite score (inverted), signal breakdown, Persona match | Weekly pull from Tacitus API post-run | Neptune uses for short idea sourcing and systematic book population
← IN | Long conviction scores | Full universe composite scores from Tacitus. Neptune can use as factor inputs for risk model — high-conviction longs may warrant different beta targets. | Weekly pull
← IN | Activist catalyst flags | Names where Tacitus detects rising activist score trend — Neptune can pre-position or flag for risk review. | Weekly pull | Forward-looking signal — use cautiously
→ OUT | Risk overlay metrics | Borrow cost %, short interest % of float, liquidity score, volatility — applied by Tacitus as risk-adjustment multiplier to final scores | Weekly push to Tacitus API post-run
→ OUT | Position sizing context | Neptune's portfolio constraint view — ensures Tacitus short flags are sized within actual portfolio limits | On-demand API call from Tacitus
MERCURY — DATA FLOWS
Direction | Data Element | Content | Mechanism | Usage in Neptune
← IN | XBRL financial signals | Revenue, EBITDA, EBITDA margin, ROIC, FCF, net debt, EV, P/B, EV/EBITDA — current and 8-quarter history. Used for factor loading computation. | Weekly ETL from Mercury XBRL pipeline | Mercury is the primary source of financial data for the factor model
← IN | Peer benchmark data | Sector × cap-tier peer medians pre-computed in Mercury. Neptune uses for factor normalization. | Weekly ETL
← IN | TSR data | 1Y and 3Y total shareholder return vs peer median. Used as momentum factor input. | Weekly ETL
→ OUT | Neptune risk overlay | Per-name risk metrics from Neptune available in Mercury company views: beta estimate, factor loadings, short interest overlay. | Post-run push to Mercury enrichment API

## Roles & Invariants
NEPTUNE — Roles, Access & System Invariants
Access control model and non-negotiable system constraints
ROLES & ACCESS CONTROL
Role | Default View | Portfolio Access | Can Approve | Cannot Do | Notes
CIO | Book of Books | All portfolios (read) | Hedge recommendations; universe filter changes; discretionary shorts | Cannot enter positions directly | Book of Books is default landing page
PM | Assigned portfolios | Full access to assigned only | Analyst ideas; discretionary shorts within mandate; forward beta overrides | Cannot modify another PM's portfolio | Can create and assign paper portfolios to analysts
Analyst | Paper portfolios | Assigned paper portfolios only | Nothing — submit ideas for PM review | Cannot modify live positions; cannot approve anything | Can manage own paper book within PM-defined permissions
Admin | All | Full access — all portfolios | All | N/A | Portfolio and user configuration; system-level settings
SYSTEM INVARIANTS — NEPTUNE NEVER DOES THESE
# | Invariant | Rationale
I-01 | Executes trades autonomously | Neptune recommends and sizes. Humans approve every position before execution. The optimizer output is a proposal, not a command.
I-02 | Uses stale prices silently | Stale price circuit breaker enforced at the Position Calculator layer (10s liquid, 60s OTC). Any stale price triggers an alert; affected P&L cells are flagged as stale, not silently recomputed.
I-03 | Conflates systematic and discretionary shorts | The short_type field flows through every layer: positions, P&L, factor exposures, optimizer runs. These two books are never aggregated into a single 'short book' figure in any report.
I-04 | Lets the optimizer modify discretionary positions | Pass 1 reads discretionary positions as inputs. The optimizer may suggest resizes (DISCRETIONARY_SUGGESTION), but cannot apply them. The PM acts on suggestions explicitly.
I-05 | Shorts a name held long in any live portfolio | Hard exclusion enforced by runtime join against all live portfolios — not a static list. Conflict flagged immediately if a long position is opened in a current systematic short.
I-06 | Applies unapproved universe filter changes | Filter change requests are stored as pending. The existing config remains active until the CIO explicitly approves. Old and new configs are timestamped in universe_filter_changes.
I-07 | Overwrites financial history | All P&L, beta, and optimizer tables are append-only. Corrections are new rows with a corrected_by reference. The audit_log captures every state transition with before/after JSON.
I-08 | Routes paper portfolio orders anywhere | Paper portfolios run the complete Neptune stack but are flagged is_paper=True throughout. No execution pathway exists; paper positions cannot be submitted to any broker or order management system.